## 运营总览
Aether Enterprise Service Operations Register
Document owner | Service Operations | Management metrics
Reporting period | 2026-08 | Metric | Target | Actual | Status | Evidence
Classification | Internal | P1 first response | ≤ 30 min | 24 | On target | INC-2026-0812
Review cadence | Monthly | P2 first response | ≤ 2 h | 105 | On target | SUP-2026-4431
Source of truth | Controlled operational register | Open high risks | 0 | 2 | Review | Risk register

## 变更台账
Change ID | Service | Classification | Planned window | Owner | Risk | Rollback owner | Approval status | Evidence
CHG-2026-0818 | Knowledge retrieval | High | 2026-08-18 20:00 | Platform Engineering | Vector index migration | SRE on-call | Approved | CAB-2026-218
CHG-2026-0820 | Identity service | Standard | 2026-08-20 21:00 | Identity Team | Certificate rotation | Identity Team | Approved | Runbook IAM-12
CHG-2026-0822 | Billing API | Normal | 2026-08-22 20:00 | API Platform | Rate-limit policy | API Platform | Pending | Peer review required
CHG-2026-0826 | Knowledge review | High | 2026-08-26 20:00 | Knowledge Team | Review workflow schema | Knowledge Team | Approved | CAB-2026-225
CHG-2026-0828 | Webhook gateway | Normal | 2026-08-28 21:00 | Integration Team | Signature validator | Integration Team | Approved | SEC-2026-091

## 风险与行动项
Risk ID | Domain | Description | Likelihood | Impact | Owner | Due date | Treatment status
RSK-001 | Identity | Legacy admin account lacks MFA evidence | Medium | High | Security Operations | 2026-08-20 | In progress
RSK-002 | Data governance | Deprecated knowledge base has no retention owner | Low | High | Data Protection | 2026-08-24 | Open
RSK-003 | RAG quality | New reranker lacks regression baseline | Medium | Medium | Model Owner | 2026-08-26 | In progress
RSK-004 | Billing | Batch client retries without idempotency key | High | Medium | API Platform | 2026-08-18 | Open
RSK-005 | Operations | P1 customer communication drill overdue | Low | Medium | Service Operations | 2026-08-30 | Planned
RSK-006 | Vendor | Webhook signing secret rotation evidence missing | Medium | Medium | Integration Team | 2026-08-22 | Open

## 服务等级
Support plan | P1 response | P2 response | Coverage | Communication | Escalation owner
Standard | 4 business hours | 1 business day | Weekdays 09:00-18:00 | Service desk | Support lead
Business | 1 hour | 4 business hours | Weekdays 08:00-22:00 | Service desk + CSM | Support lead
Enterprise | 30 minutes | 2 hours | 24×7 | Status page + named contacts | Incident commander